## Insecure IT Testmodell
Severity | Likelihood | Impact | STRIDE | Function | CWE | Risk Category | Technical Asset | Communication Link | RAA % | Identified Risk | Action | Mitigation | Check | ID | Status | Justification | Date | Checked by | Ticket
Elevated | Likely | Medium | Tampering | Development | CWE-79 | Cross-Site Scripting (XSS) | app |  | 30 | Cross-Site Scripting (XSS) risk at app | XSS Prevention | Try to encode all values sent back to the browser and also handle DOM-manipulations in a safe way to avoid DOM-based XSS. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-scripting@app | Unchecked
Elevated | Likely | Medium | Tampering | Development | CWE-79 | Cross-Site Scripting (XSS) | webapp |  | 1 | Cross-Site Scripting (XSS) risk at webapp | XSS Prevention | Try to encode all values sent back to the browser and also handle DOM-manipulations in a safe way to avoid DOM-based XSS. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-scripting@webapp | Unchecked
Elevated | Likely | Medium | Elevation of Privilege | Architecture | CWE-306 | Missing Authentication | app | to-app | 30 | Missing Authentication covering communication link to-app from webapp to app | Authentication of Incoming Requests | Apply an authentication method to the technical asset. To protect highly sensitive data consider the use of two-factor authentication for human users. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-authentication@webapp>to-app@webapp@app | Unchecked
Elevated | Likely | Medium | Elevation of Privilege | Architecture | CWE-306 | Missing Authentication | database | to-database | 100 | Missing Authentication covering communication link to-database from app to database | Authentication of Incoming Requests | Apply an authentication method to the technical asset. To protect highly sensitive data consider the use of two-factor authentication for human users. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-authentication@app>to-database@app@database | Unchecked
Elevated | Likely | Medium | Elevation of Privilege | Architecture | CWE-306 | Missing Authentication | webapp | to-webapp | 1 | Missing Authentication covering communication link to-webapp from client to webapp | Authentication of Incoming Requests | Apply an authentication method to the technical asset. To protect highly sensitive data consider the use of two-factor authentication for human users. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-authentication@client>to-webapp@client@webapp | Unchecked
Elevated | Very Likely | Medium | Tampering | Development | CWE-89 | SQL/NoSQL-Injection | app | to-database | 30 | SQL/NoSQL-Injection risk at app against database database via to-database | SQL/NoSQL-Injection Prevention | Try to use parameter binding to be safe from injection vulnerabilities. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | sql-nosql-injection@app@database@app>to-database | Unchecked
Elevated | Likely | Medium | Information Disclosure | Operations | CWE-319 | Unencrypted Communication | webapp | to-app | 1 | Unencrypted Communication named to-app between webapp and app | Encryption of Communication Links | Apply transport layer encryption to the communication link. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-communication@webapp>to-app@webapp@app | Unchecked
Elevated | Likely | Medium | Information Disclosure | Operations | CWE-319 | Unencrypted Communication | client | to-webapp | 1 | Unencrypted Communication named to-webapp between client and webapp | Encryption of Communication Links | Apply transport layer encryption to the communication link. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-communication@client>to-webapp@client@webapp | Unchecked
Medium | Unlikely | Medium | Information Disclosure | Operations | CWE-319 | Unencrypted Communication | app | to-database | 30 | Unencrypted Communication named to-database between app and database | Encryption of Communication Links | Apply transport layer encryption to the communication link. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-communication@app>to-database@app@database | Unchecked
Medium | Very Likely | Low | Spoofing | Development | CWE-352 | Cross-Site Request Forgery (CSRF) | app | to-app | 30 | Cross-Site Request Forgery (CSRF) risk at app via to-app from webapp | CSRF Prevention | Try to use anti-CSRF tokens ot the double-submit patterns (at least for logged-in requests). When your authentication scheme depends on cookies (like session or token cookies), consider marking them with the same-site flag. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-request-forgery@app@webapp>to-app | Unchecked
Medium | Very Likely | Low | Spoofing | Development | CWE-352 | Cross-Site Request Forgery (CSRF) | webapp | to-webapp | 1 | Cross-Site Request Forgery (CSRF) risk at webapp via to-webapp from client | CSRF Prevention | Try to use anti-CSRF tokens ot the double-submit patterns (at least for logged-in requests). When your authentication scheme depends on cookies (like session or token cookies), consider marking them with the same-site flag. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | cross-site-request-forgery@webapp@client>to-webapp | Unchecked
Medium | Unlikely | Medium | Tampering | Architecture | CWE-1127 | Missing Build Infrastructure | app |  | 30 | Missing Build Infrastructure in the threat model (referencing asset app as an example) | Build Pipeline Hardening | Include the build infrastructure in the model. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-build-infrastructure@app | Unchecked
Medium | Likely | Low | Tampering | Operations | CWE-16 | Missing Hardening | database |  | 100 | Missing Hardening risk at database | System Hardening | Try to apply all hardening best practices (like CIS benchmarks, OWASP recommendations, vendor recommendations, DevSec Hardening Framework, DBSAT for Oracle databases, and others). | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-hardening@database | Unchecked
Medium | Unlikely | Medium | Elevation of Privilege | Business Side | CWE-308 | Missing Two-Factor Authentication (2FA) | webapp | to-webapp | 1 | Missing Two-Factor Authentication covering communication link to-webapp from client to webapp | Authentication with Second Factor (2FA) | Apply an authentication method to the technical asset protecting highly sensitive data via two-factor authentication for human users. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-authentication-second-factor@client>to-webapp@client@webapp | Unchecked
Medium | Unlikely | Medium | Information Disclosure | Architecture | CWE-522 | Missing Vault (Secret Storage) | app |  | 30 | Missing Vault (Secret Storage) in the threat model (referencing asset app as an example) | Vault (Secret Storage) | Consider using a Vault (Secret Storage) to securely store and access config secrets (like credentials, private keys, client certificates, etc.). | Is a Vault (Secret Storage) in place? | missing-vault@app | Unchecked
Medium | Likely | Low | Information Disclosure | Development | CWE-918 | Server-Side Request Forgery (SSRF) | webapp | to-app | 1 | Server-Side Request Forgery (SSRF) risk at webapp server-side web-requesting the target app via to-app | SSRF Prevention | Try to avoid constructing the outgoing target URL with caller controllable values. Alternatively use a mapping (whitelist) when accessing outgoing URLs instead of creating them including caller controllable values. When a third-party product is used instead of custom developed software, check if the product applies the proper mitigation and ensure a reasonable patch-level. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | server-side-request-forgery@webapp@app@webapp>to-app | Unchecked
Medium | Unlikely | Medium | Information Disclosure | Operations | CWE-311 | Unencrypted Technical Assets | app |  | 30 | Unencrypted Technical Asset named app | Encryption of Technical Asset | Apply encryption to the technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-asset@app | Unchecked
Medium | Unlikely | Medium | Information Disclosure | Operations | CWE-311 | Unencrypted Technical Assets | client |  | 1 | Unencrypted Technical Asset named client | Encryption of Technical Asset | Apply encryption to the technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-asset@client | Unchecked
Medium | Unlikely | Medium | Information Disclosure | Operations | CWE-311 | Unencrypted Technical Assets | database |  | 100 | Unencrypted Technical Asset named database | Encryption of Technical Asset | Apply encryption to the technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-asset@database | Unchecked
Medium | Unlikely | Medium | Information Disclosure | Operations | CWE-311 | Unencrypted Technical Assets | webapp |  | 1 | Unencrypted Technical Asset named webapp | Encryption of Technical Asset | Apply encryption to the technical asset. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unencrypted-asset@webapp | Unchecked
Medium | Very Likely | Low | Elevation of Privilege | Architecture | CWE-501 | Unguarded Access From Internet | app | to-app | 30 | Unguarded Access from Internet of app by webapp via to-app | Encapsulation of Technical Asset | Encapsulate the asset behind a guarding service, application, or reverse-proxy. For admin maintenance a bastion-host should be used as a jump-server. For file transfer a store-and-forward-host should be used as an indirect file exchange platform. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | unguarded-access-from-internet@app@webapp@webapp>to-app | Unchecked
Low | Unlikely | Low | Elevation of Privilege | Operations | CWE-1008 | Missing Network Segmentation | database |  | 100 | Missing Network Segmentation to further encapsulate and protect database against unrelated lower protected assets in the same network segment, which might be easier to compromise by attackers | Network Segmentation | Apply a network segmentation trust-boundary around the highly sensitive assets and/or datastores. | Are recommendations from the linked cheat sheet and referenced ASVS chapter applied? | missing-network-segmentation@database | Unchecked
Low | Unlikely | Low | Tampering | Operations | CWE-1008 | Missing Web Application Firewall (WAF) | app |  | 30 | Missing Web Application Firewall (WAF) risk at app | Web Application Firewall (WAF) | Consider placing a Web Application Firewall (WAF) in front of the web-services and/or web-applications. For cloud environments many cloud providers offer pre-configured WAFs. Even reverse proxies can be enhances by a WAF component via ModSecurity plugins. | Is a Web Application Firewall (WAF) in place? | missing-waf@app | Unchecked
Low | Unlikely | Low | Tampering | Operations | CWE-1008 | Missing Web Application Firewall (WAF) | webapp |  | 1 | Missing Web Application Firewall (WAF) risk at webapp | Web Application Firewall (WAF) | Consider placing a Web Application Firewall (WAF) in front of the web-services and/or web-applications. For cloud environments many cloud providers offer pre-configured WAFs. Even reverse proxies can be enhances by a WAF component via ModSecurity plugins. | Is a Web Application Firewall (WAF) in place? | missing-waf@webapp | Unchecked